## Milestones
Milestone | Buổi | Thời gian | Deliverables
M1: Project Setup | 2025-01-03 | 27/11-11/12/2025 | Requirements, DB Design, Environment
M2: Backend Foundation | 2025-04-08 | 18/12/2025-15/01/2026 | Auth, APIs, Core Logic
M3: Mobile App MVP | 2025-09-15 | 22/01-12/03/2026 | Student/Teacher Mobile App
M4: Advanced Features | 16-20 | 19/03-16/04/2026 | QR, WebSocket, Admin Dashboard
M5: Testing & Deploy | 21-24 | 23/04-14/05/2026 | Production-Ready Application

## Gantt Chart
Công việc | Bắt đầu | Kết thúc | Giai đoạn | B1 | B2 | B3 | B4 | B5 | B6 | B7 | B8 | B9 | B10 | B11 | B12 | B13 | B14 | B15 | B16 | B17 | B18 | B19 | B20 | B21 | B22 | B23 | B24
Requirements Analysis |  |  | Planning | bar: B1 to B2
Database Design |  |  | Planning | bar: B2 to B3
Backend Setup |  |  | Backend | bar: B4 to B5
Authentication |  |  | Backend | bar: B5 to B6
User Management API |  |  | Backend | bar: B6 to B7
Class & Session API |  |  | Backend | bar: B7 to B8
Mobile App Foundation |  |  | Mobile | bar: B9 to B11
Student Features |  |  | Mobile | bar: B11 to B13
Teacher Features |  |  | Mobile | bar: B13 to B15
QR Code System |  |  | Advanced | bar: B16 to B17
WebSocket Real-time |  |  | Advanced | bar: B17 to B18
Admin Dashboard |  |  | Advanced | bar: B18 to B20
Integration Testing |  |  | Testing | bar: B21 to B22
Bug Fixes |  |  | Testing | bar: B22 to B23
Production Deploy |  |  | Deploy | bar: B23 to B24

## Lịch 24 Buổi
Buổi | Ngày (Thứ 4) | Tháng/Năm | Giai đoạn | Milestone
Buổi 1 | 27/11/2025 | 2025-11-01